## Gantt Chart
FOOD FORWARD DATABASE PROJECT PLAN
PROJECT TITLE |  | Food Forward Database |  |  |  |  | COMPANY NAME | [6 empty] | Food Forward
PROJECT MANAGER |  | Sabona Abubeker, Kainoa Borges, Angela McNeese |  |  |  |  | DATE | [6 empty] | 2022-09-06
WBS NUMBER | TASK TITLE | TEAM LEAD | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
[7 empty] | WEEK 1 9/5-9/9 |  |  |  |  | WEEK 2 9/12-9/16 |  |  |  |  | WEEK 3 9/19-9/23 |  |  |  |  | WEEK 4 9/26-9/30 |  |  |  |  | WEEK 5 10/3-10/7 |  |  |  |  | WEEK 6 10/10-10/14 |  |  |  |  | WEEK 7 10/17-10/21 |  |  |  |  | WEEK 8 10/24-10/28 |  |  |  |  | WEEK 9 10/31-11-4 |  |  |  |  | WEEK 10 11/7-11/11 |  |  |  |  | WEEK 11 11/14-11/18 |  |  |  |  | WEEK 12 11/21-11/25 |  |  |  |  | WEEK 13 11/28-12/2 |  |  |  |  | WEEK 14 12/5-12/9 |  |  |  |  | WEEK 15 12/12-12/16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Planning and Requirements
1.1 | Schedule First Client Meeting | Kainoa B | 2022-09-05 | 2022-09-06 | 1 | 100% | bar: WEEK 1 9/5-9/9 M; WEEK 1 9/5-9/9 F
1.1.1 | Project Charter Revisions | Kainoa B | 2022-09-06 | 2022-09-06 | 0 | 100% | bar: WEEK 1 9/5-9/9 T
1.2 | Initial Client Meeting | Kainoa B | 2022-09-09 | 2022-09-09 | 0 | 100% | bar: WEEK 1 9/5-9/9 F; WEEK 3 9/19-9/23 M to WEEK 3 9/19-9/23 R
1.3 | Requirements Outline | All | 2022-09-09 | 2022-09-21 | 12 | 100% | bar: WEEK 1 9/5-9/9 F to WEEK 3 9/19-9/23 W
1.4 | Functional Requirements Defined | All | 2022-09-16 | 2022-09-21 | 5 | 100% | bar: WEEK 2 9/12-9/16 F to WEEK 3 9/19-9/23 W
1.5 | User Stories/Use Cases | Sabona A | 2022-09-16 | 2022-09-21 | 5 | 100% | bar: WEEK 2 9/12-9/16 F to WEEK 3 9/19-9/23 R
1.6 | Interfaces and Functions Planned | Sabona A | 2022-09-16 | 2022-09-21 | 5 | 100% | bar: WEEK 2 9/12-9/16 F to WEEK 3 9/19-9/23 W
1.7 | Requirements Document Complete | Sabona A | 2022-09-21 | 2022-09-22 | 1 | 100% | bar: WEEK 3 9/19-9/23 M to WEEK 3 9/19-9/23 R
1.8 | Diagrams | Sabona A | 2022-09-21 | 2022-09-28 | 7 | 100% | bar: WEEK 3 9/19-9/23 M to WEEK 4 9/26-9/30 W
2 | Development
2.1 | Software Recommendation Presentation | Angela M. | 2022-10-05 | 2022-10-07 | 10 | 100% | bar: WEEK 4 9/26-9/30 M to WEEK 5 10/3-10/7 F
2.2 | Instructions to set up server | Sabona A. | 2022-10-13 | 2022-10-13 | 5 | 100% | bar: WEEK 4 9/26-9/30 M to WEEK 4 9/26-9/30 F; WEEK 5 10/3-10/7 F to WEEK 6 10/10-10/14 F
2.3 | Setting up Database Environment on the server | Prakash J. | 2022-10-17 | 2022-10-20 | 3 | 100% | bar: WEEK 4 9/26-9/30 M to WEEK 4 9/26-9/30 F; WEEK 6 10/10-10/14 T to WEEK 6 10/10-10/14 F
2.4 | Structuring the database | Angela M. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.1 | Database Entities Set #1 | Kainoa B. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.2 | Database Entities Set #2 | Sabona A. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.3 | Database Entities Set #3 | Angela M. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.4 | Database Relationships Set #1 | Kainoa B. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.5 | Database Relationships Set #2 | Sabona A. | 2022-10-20 | 2022-10-21 | 1 | 100% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.4.6 | Database Relationships Set #3 | Angela M. | 2022-10-20 | 2022-10-21 | 1 | 95% | bar: WEEK 7 10/17-10/21 T to WEEK 9 10/31-11-4 M
2.5 | Pseudocode Data functions and front end code | Angela M. | 2022-10-21 | 2022-10-24 | 3 | 100% | bar: WEEK 4 9/26-9/30 M to WEEK 4 9/26-9/30 F; WEEK 5 10/3-10/7 W to WEEK 7 10/17-10/21 W
2.5.1 | Set up localhost website code and instructions on github |  |  |  | 0 | 100%
2.5.2 | Mock up the page layouts | ALL | 2022-10-21 | 2022-11-04 | 13 | 75%
2.5.2.1 | Mobile Layouts | Angela M. | 2022-10-21 | 2022-10-26 | 5 | 95%
2.5.2.2 | Tablet Layouts | Angela M. | 2022-10-21 | 2022-10-30
2.5.2.3 | Desktop Layout | Sabona A. | 2022-10-21 | 2022-10-26 | 5 | 100%
2.5.3 | Fixing the ER diagram | Kainoa B. | 2022-10-24 | 2022-10-25 | 1 | 100%
2.5.4 | New Normalization Diagrams | Kainoa B. | 2022-10-24 | 2022-10-26 | 2 | 100%
2.5.4.1 | Fixed ER Diagram Started | ALL | 2022-11-01 | 2022-11-01 | 1 | 100%
2.5.5 | Database Revision Set #1 | Kainoa B. | 2022-11-02 | 2022-11-04 | 2 | 100%
2.5.6 | Database Revision Set #2 | Kainoa B. | 2022-11-04 | 2022-11-06 | 2 | 100%
2.5.7 | Database Revision Set #3 | Kainoa B. | 2022-11-06 | 2022-11-07 | 1 | 100%
2.5.8 | SQL Query Set #1 | Kainoa B. | 2022-11-07 | 2022-11-08 | 1 | 100%
2.5.9 | SQL Query Set #2 | Kainoa B. | 2022-11-07 | 2022-11-08 | 1 | 100%
2.5.10 | SQL Query Set #3 | Angela M. | 2022-11-09 | 2022-11-11 | 2 | 100%
2.8 | Software Interfaces |  |  |  | 0 | 0%
2.8.1 | Report Page | Angela M. | 2022-11-01 |  | -44221 | 0%
2.8.2 | Report Generation | Angela M. |  |  | 0 | 0%
2.8.3 | Meal Plan Report | Sabona A. | 2022-11-18 | 2022-11-23 | 5 | 100%
2.8.4 | Meal Report | Sabona A. | 2022-11-23 | 2022-11-25 | 2 | 100%
2.8.5 | Packaging Report | Angela M. |  |  | 0 | 0%
2.8.6 | Household Report | Kainoa B. | 2022-11-16 | 2022-11-20 | 4 | 95%
2.8.7 | Inventory Management Page | Kainoa B. | 2022-11-16 | 2022-11-20 | 4 | 95%
2.8.8 | Unit Information | Kainoa B. |  |  | 0 | 0%
2.8.9 | Household Management Page | Kainoa B, | 2022-11-17 | 2022-11-21 | 4 | 100%
2.8.10 | Package Information | Angela M. | 2022-11-17 | 2022-11-21 | 4 | 100%
2.8.11 | Recipe Management Page | Sabona A. | 2022-11-20 | 2022-11-23 | 3 | 100%
2.8.12 | Expense Management Page | Angela M. |  |  | 0 | 0%
2.9 | Functions |  |  |  | 0 | 0%
2.9.3 | Authenticate User | Angela M. |  |  | 0 | 0%
2.9.1 | New Entry to SQL | ALL | 2022-11-17 | 2022-11-22 | 5 | 100%
2.9.2 | Execute Query | ALL | 2022-11-17 | 2022-11-22 | 5 | 100%
2.9.4 | Ingredients From Processing | Kainoa B. |  |  | 0 | 0%
2.9.5 | Meal From Processing | Sabona A. | 2022-11-19 | 2022-11-22 | 3 | 0%
2.9.6 | Inventory From Processing | Kainoa B. | 2022-11-18 | 2022-11-20 | 2 | 95%
2.9.7 | Household from Processing | Kainoa B. | 2022-11-18 | 2022-11-20 | 2 | 95%
2.9.8 | Unit Conversion | Angela M. |  |  | 0 | 0%
2.9.9 | Calculate Servings Required | Angela M. |  |  | 0 | 0%
2.9.10 | Calculate Meal Quantity Required |  |  |  | 0 | 0%
2.9.11 | Calculate Ingredient Grand Total | Kainoa B. |  |  | 0 | 0%
2.9.12 | Packaging Supply Sizes | Angela M. |  |  | 0 | 0%
2.6 | External Interfaces |  |  |  | 0 | 0%
2.6.1 | Login Screen/Container | Angela M. | 2022-11-23 | 2022-11-25 | 2 | 100%
2.6.2 | Universal Navbar | Kainoa B. | 2022-11-20 | 2022-11-22 | 2 | 100%
2.7 | User Interfaces |  |  |  | 0 | 0%
2.7.1 | Account Page | Sabona A. | 2022-11-24 | 2022-11-26 | 2 | 100%
2.7.2 | Admin Page | Angela M. | 2022-11-25 | 2022-11-27 | 2 | 100%
0%
3 | Testing
3.1 | Testing Data Input Functions |  | 2022-11-28 | 2022-12-13 | 15 | 95% | bar: WEEK 9 10/31-11-4 T to WEEK 10 11/7-11/11 T
3.1.1 | Inventory Management Page | Kainoa B. | 2022-11-28 | 2022-11-30 | 2 | 100%
3.1.2 | Unit Information | Kainoa B. |  |  |  | 0%
3.1.3 | Household Management Page | Kainoa B. | 2022-11-30 | 2022-12-02 | 3 | 100%
3.1.4 | Package Information | Angela M. | 2022-11-28 | 2022-11-29 | 1 | 100%
3.1.5 | Recipe Management Page | Sabona A. | 2022-11-28 | 2022-11-30 | 2 | 100%
3.1.6 | Expense Management Page | Angela M. |  |  |  | 0%
3.1.7 | New Entry to SQL | ALL | 2022-11-28 | 2022-12-01 | 3 | 100%
3.1.8 | Execute Query | ALL | 2022-11-28 | 2022-12-01 | 3 | 100%
3.1.9 | Ingredients From Processing | Kainoa B. | 2022-11-30 | 2022-12-01 | 1 | 100%
3.1.10 | Meal From Processing | Sabona A. | 2022-11-30 | 2022-12-02 | 2 | 100%
3.1.11 | Inventory From Processing | Kainoa B. |  |  |  | 100%
3.1.12 | Household from Processing | Kainoa B. |  |  |  | 100%
3.2 | Testing Data Output and Report Functions |  | 2022-12-01 | 2022-12-08 | 7 | 90% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
3.2.1 | Report Generation | Angela M. | 2022-12-03 | 2022-12-05 | 2 | 100%
3.2.2 | Meal Plan Report | Sabona A. | 2022-12-02 | 2022-12-07 | 5 | 100%
3.2.3 | Meal Report | Sabona A. | 2022-12-05 | 2022-12-09 | 4 | 100%
3.2.4 | Packaging Report | Angela M. | 2022-12-08 | 2022-12-10 | 2 | 100%
3.2.5 | Household Report | Kainoa B. | 2022-12-09 | 2022-12-11 | 2 | 100%
3.2.6 | [5 empty] | 0% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
3.3 | Presentation on Prototype | ALL | 2022-12-09 | 2022-12-14 | 5 | 90% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
0% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
0% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
0% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
0% | bar: WEEK 9 10/31-11-4 W to WEEK 10 11/7-11/11 T
3.5 | User testing |  | 2022-11-12 | 2022-11-14 | 2 | 0% | bar: WEEK 10 11/7-11/11 R to WEEK 11 11/14-11/18 M
4 | Deployment
4.1 | Input given data into Database |  | 2022-11-14 | 2022-11-16 | 2 | 0% | bar: WEEK 11 11/14-11/18 M to WEEK 11 11/14-11/18 W
4.2 | Finalize with Debi |  | 2022-11-15 | 2022-11-17 | 2 | 0% | bar: WEEK 11 11/14-11/18 T to WEEK 11 11/14-11/18 R
4.3 | Finalize Prototype/Overview with Client |  | 2022-11-17 | 2022-11-19 | 2 | 0% | bar: WEEK 11 11/14-11/18 R to WEEK 11 11/14-11/18 F
4.4 | Release Prototype |  | 2022-11-21 | 2022-12-17 | 2 | 0%

## Sheet2
Database Table Sets |  |  |  |  | Database Relationship Sets
1 | PACKAGE | REQ_PACKAGE | HOUSEHOLD | ADDRESS | 1 | ADDRESS<->HOUSEHOLD<->PACKAGE_LIST<->PACKAGE
2 | MEAL_PLAN | MEAL | INGREDIENT_LIST | HH_LIST | 2 | MEAL<->MEAL_PLAN<->HH_LIST
3 McNeese | INGREDIENT_ITEM | INGREDIENT_TYPE | SUPPLIER |  | 3 | INGREDIENT_LIST<->INGREDIENT_ITEM<->INGREDIENT_TYPE | INGREDIENT_ITEM<->SUPPLIER
Reports
Meal Report | Meal Name | Ingredients | Ingredient quantities
Shopping Report | Ingredients in stock | Ingredients used | Cost of Ingredients Used | Ingredients to buy | Cost of Ingredients to Buy
Household Report | Households | Meals required | Cost of Packages Used | Snacks required | Packaging required | Cost of Packages to Buy
Packaging Report | Packages in stock | Packages used | Packages to buy
End of Week Totals | Total Ingredient cost | Total Package cost
Pages To Implement |  |  |  |  | Final Checklist
Sabona | Page Set 1: | Account Creation | Meal Recipe | Meal Plan | 2.1.2.1 Login Screen | not comparing input to db users
Angela | Page Set 2: | Ingredients to Purchase | Packaging to Purchase | Station List | Username/PW reset | not comparing input to db users
Kainoa | Page Set 3: | Packaging List | Packaging Inventory |  | Menu Item/Recipe Access
Menu Selection/ Meal Plan Screen
Pages To Do: | Sign In | User Page | HH Labels |  | Ingredient Tracking | sync to db
[5 empty] | Household Tracking | Working - not on the vm
Pages Mostly Done: | Ingredient Inventory | Households | User Page | Ingredients List | Report Generation | add individual reports pages
| Menu | Landing/Welcome | Forgot Username/Password |  | Expense/Cost Tracking | Handling in reports -
HTTP/HTTPS
Admin User
Pages Fully Done |  |  |  | Angela | Basic User | Add/edit functions need to be reserved for admin users
[5 empty] | Reports | Page build, HH report page linked, output... needs to be formatted
Site Adaptation Requirements
[5 empty] | 2.2.1 Households | Working - not on the vm
|  |  |  | Angela | Household Calculation | Get all households not paused -> Assign meals to those households | Get all meals assigned to households | Multiply servings by #adults(1) #children(.5)
2.2.2 Menu Items
|  |  | Kainoa | By 12-11 | Ingredients Inventory
|  |  | Kainoa | By 12-11 | Packaging Inventory
[5 empty] | Conversions | Last Priority
[5 empty] | Reports | Page exists, link to reports as they are built: 1/12 so far
3.1.1 Login Screen
Login Container
Universal Navbar
|  |  |  | Angela | User Interfaces
|  |  | Sabona |  | - Account page | Outlined, needs way to get current user info. Still probably better as a django/react function than a db if we can swing it
- Admin Page
3.1.5.0 Report Page
|  |  | Sabona |  | Meal Report
Packaging Report
|  |  | Kainoa | By 12-11 | Household Report
Inventory Management Page
3.1.7 Recipe Management Page
3.1.8 HH Management Page
|  |  | Kainoa |  | 3.1.9 Packaging Info
New SQL entry
[5 empty] | Execute Query | execute_query() implemented
Auth. User
Ingredients Form Processing
Meal Form Processing
Inventory Form Processing
HH form processing
[5 empty] | 3.2.9 Unit Conversion | Last priority
|  |  | Kainoa |  | 3.2 10 Calculate Servings Required | Handling with Household calculation
|  |  | Kainoa |  | 3.2.11 Calculate Meal Quantity Required | Handling with Household calculation
3.2.14 Meal Plan
[5 empty] | Station List | Created: needs data pulled in from other tables (not stations)
Puchasing List: Pack
Purchasing List: Ingred.
Household Labels

## MySQL Queries
Page |  | WHAT TO FIND | SQL QUERIES
NOTE: <descriptor> == replace with actual data
Sign In | Output Good
Check User/pw | Accept/Reject | This user's password | SELECT password FROM users WHERE username = <input username> |  | Added new USERS table in the database with u_id, username, password, and admin_flag
Remember me |  |  | Can be done with cookies but I'm not sure how Django handles that
Account Creation
Submit new user to db |  |  | INSERT INTO users (username, password, admin_flag) VALUES {<input username>, <input password>, <0 or 1>}
Welcome Screen
All navigation links |  |  | Handling with React (Sort of a Single Page Application where 'pages' refers to collections of content on screen at one time)
User Page | Output Good
Query User info |  | Get all user info | SELECT username, password, admin_flag FROM users |  | Do we need more user information?
|  | Update a user's info | UPDATE users SET username=<input username>, password=<input password>, admin_flag=<0 or 1>
Ingredients List | Output Good
Query Table | show results | All ingredients | SELECT i.*, s.s_name |  | qty_on_hand is derived and may need more queries to work.
|  | This ingredient's supplier | FROM ingredients i
|  | This ingredient's pref supplier | INNER JOIN supplier s
WHERE i.isupplier_id = s.s_id
OR i.pref_isupplier_id = s.s_id
Menu | Output Good | Built
Query Meals w dates | show meal names | All meals and dates | SELECT mp.m_date, r.r_name
|  | This meal recipe's name | FROM meal_plans mp
|  | This snack recipe's name | INNER JOIN recipes r
ON mp.meal_r_num = r.r_num
OR mp.snack_r_num = r.r_num
WHERE r.r_name = "pizza" OR mp.m_date = "22/11/7"
Meal Recipe Page | Output Good << Needs Instructions Added>>
Query from link? |  | All recipe names and numbers | SELECT mp.m_date, ri.prep, ri.amt, ri.unit, i.ingredient_name, ra.allergy, rd.diet_category | Doesnt quite work
|  | Ascending list of instructions | FROM ingredients AS i JOIN recipe_ingredients AS ri ON i.i_id = ri.ri_ing_id | May be better to break it up into several queries once we have a clear idea of how it will be called
|  | List of ingredients | JOIN recipes AS r on ri.ri_recipe_num = r.r_num
|  | List of allergies | JOIN meal_plans AS mp ON r.r_num = mp.meal_r_num OR r.r_num = mp.snack_r_num
|  | List of diets | LEFT JOIN recipe_allergies ra ON ra.ra_recipe_num = r.r_num
LEFT JOIN recipe_diets rd ON rd.rd_recipe_num = r.r_num
WHERE r.r_name = "pizza" OR mp.m_date = "22/11/7"
#JOIN recipe_instructions rin ON rin.inst_recipe_num = r.r_num
Households | Output Good
Query all hh_name | show household information | Select/Sort | SELECT hh_name, num_adult, num_child FROM households
Packaging List | Output Good
Query all packaging |  | Select/Sort | SELECT p_id, package_type, unit_qty, qty_on_hand FROM packaging
Forgot User/pw
Check for username email, send email |  |  | TBH this would be better handled by something more secure
Meal List | Output Good
Query db for meal_name (date?) |  |  | SELECT * FROM recipes WHERE r_name = "pizza"
Ingredients Inventory | Output Good
Query for keyword? |  | Select/Sort | SELECT * FROM ingredients WHERE ingredient_name = "user_input"
#WHERE qty_on_hand > 0 # Probably better to just display 0
Meal Plan | Output Good
Query by date |  | output meals and snacks planned | SELECT mp.m_date, r.r_name
FROM meal_plans mp
JOIN recipes r
ON r.r_num = mp.meal_r_num OR r.r_num = mp.snack_r_num
WHERE m_date = "22/11/7"
Packaging Inventory | Output Good
Query by keyword |  | select/sort | SELECT * FROM packaging WHERE package_type = "user input"
#WHERE qty_on_hand > 0
Ingredients: Purchasing List | x Servings needed
Query dates or meal name | check inventory on hand | subtract on_hand and output | SELECT i.ingredient_name, ri.amt, ri.unit, ri.prep | Multiply by servings needed
FROM recipes AS r
JOIN recipe_ingredients AS ri
ON ri.ri_recipe_num = r.r_Num
JOIN ingredients AS i
ON ri.ri_ing_id = i.i_id
WHERE r.r_num = "104"
Packaging: Purchasing List | x Servings needed
Query date range for meals planned | retrieve packaging requirements | subtract on_hand and output | SELECT rp.amt, p.unit_qty, p.unit, p.package_type, p.qty_on_hand, p.psupplier_id, p.pref_psupplier_id | Multiply by servings needed
FROM recipes AS r
JOIN recipe_packaging AS rp ON rp.rp_recipe_num = r.r_Num
JOIN packaging AS p ON rp.rp_id = p.p_id
WHERE r.r_num = "102"
Generate Station Lists | Output Good
Query Date range to populate meals list | get hh servings and meal packaging | generate labels and output | SELECT mp.m_date, meal_hh_name, num_servings, rp.amt, rp.pkg_type,ri.amt, ri.unit, i.ingredient_name, ri.prep
|  | Number of families/ servings | FROM ingredients AS i JOIN recipe_ingredients AS ri ON i.i_id = ri.ri_ing_id
|  | Ingredients and packaging lists | JOIN recipes AS r on ri.ri_recipe_num = r.r_num
JOIN meal_plans AS mp ON r.r_num = mp.meal_r_num OR r.r_num = mp.snack_r_num
JOIN hh_meal_plans AS hmp ON meal_id = m_id
JOIN households AS hh ON hmp.meal_hh_name = hh.hh_name
JOIN recipe_packaging AS rp ON rp.rp_ing_id = ri.ri_ing_id
WHERE m_date = "22/11/7"
Generate Household Labels
Query date range | get hh's scheduled, return packaging #s | generate labels | SELECT hh_name, num_adult, num_child FROM household WHERE
JOIN meal_plan, hh_meal_plan ON meal_id, m_id WHERE meal_date = "user_input"
JOIN hh_meal_plan, household ON hh_id, m_id WHERE meal_date = "user_input"
Packaging Summary | Output Good
Query date range or Meal name | get meals and packaging #s per | select/sort | SELECT mp.m_date, meal_hh_name, num_servings, rp.amt, rp.pkg_type
FROM meal_plans AS mp JOIN recipes r
ON r.r_num = mp.meal_r_num OR r.r_num = mp.snack_r_num
JOIN hh_meal_plans AS hmp ON hmp.meal_id = m_id
JOIN recipe_packaging AS rp ON rp.rp_recipe_num = r.r_num
WHERE m_date = "22/11/7"
Meal Prep Instructions
tbd
Drop down Menu choices
Menu_names/Snacks
Ingredients(too long?)
Returnable packaging
Household Names
Dates